April 18, 2019

Nevada State Board of Education

Dear State Board Members:

Because my tenure as State Superintendent of Public Instruction began on April 2, 2019, I have elected to resubmit the 2018 State Improvement Plan (STIP) for 2019. Rather than rush through a hurried process with very little context during my very short tenure here, I believe updating the STIP deserves a thorough review. In reading the current plan, there were no major concerns in the solid work that was completed before my arrival. Please note that the Department has reviewed the 2018 STIP and updated items as needed, such as updating the most recent baseline data for annual progress. I am grateful for the decision made by my predecessor allowing me to make any changes I see fit in the STIP going forward.

Resubmitting the 2018 STIP will also allow for the Department of Education to complete the work required by the ongoing legislative session. By the time the Department submits the next STIP in March of 2020, it will reflect the direction we have been given by the Governor and Legislature. Over the course of the coming year, I will also have an opportunity to observe and assess the current plan as well as review current student data. Equally important, I will have an opportunity to engage stakeholders and receive input from districts around the state.

Sincerely,

Jhone M. Ebert

Superintendent of Public Instruction

# INTRODUCTION

State law requires the Nevada State Board of Education to develop an annual plan to improve the achievement of pupils enrolled in Nevada public schools. This plan, commonly referred to as the “State Improvement Plan,” or “STIP,” is prepared for State Board’s consideration by the Superintendent of Public Instruction, the staff of the Department of Education, and a variety of stakeholders. The focus of this year’s plan serves as an update to previous STIP submissions, with an emphasis on college and career readiness of all students in the P-12 public education system, alignment to Nevada’s Every Student Succeeds Act Consolidated State Plan, the Department’s Five-Year Strategic Plan, which was adopted by the State Board in December of 2016, and the welcoming of a new Superintendent, Jhone Ebert. Superintendent Ebert’s decision to update the 2018 STIP for a 2019 submission was informed by a willingness to engage with both internal and external stakeholders before embarking on significant changes to the State’s strategic plan.

In the past, Nevada stakeholders came together to set a bold but achievable goal to become the fastest improving state in the nation. As the Department’s programs evolve through the continued implementation of a historic suite of education programs and initiatives passed in 2015, The Department recognizes that this plan reflects our continued effort in making sure Nevada’s educators and students are truly ready for success.

Pursuant to NRS 385.3593 and Assembly Bill 30 from the 2015 Legislative Session, the plan must contain at least the following components:

- A review and analysis of student data collected by the Department;

- The identification of any problems or factors common among school districts or charter schools;

- Strategies to improve student achievement;

- Strategies to provide information about higher education and financial aid;

- Strategies to improve the allocation of resources, including information on the effectiveness of legislative appropriations related to education; and

- Clearly defined goals and benchmarks.

In addition to these requirements, Superintendent Ebert is including an emphasis on identifying and supporting areas of low performance across school districts and charter schools as well as strategies for students completing the FAFSA (Free Application for Federal Student Aid) as a way to provide information about higher education and financial aid.

The plan must also include an identification of Department staff responsible for ensuring strategies are successful, timelines and measurable criteria for determining such success, and a budget for the overall cost of carrying out the plan.

Resubmitting the 2018 STIP allows  the Department and its staff to complete the Legislative Session and reflect on the Department’s strategic planning efforts before unveiling a STIP under the Superintendent’s signature in March 2020. Like its predecessors, this document adheres as closely as possible to statutory requirements, is focused solely on calendar year 2019, and seeks to provide the next step in the state’s future plan amendments. The plan is limited to certain ongoing key activities of the Departmentand new initiatives the Department is beginning to implement.

# ABOUT THE DEPARTMENT OF EDUCATION

Nevada’s Department of Education consists of the State Board, the Superintendent of Public Instruction, approximately 180 employees, and more than a dozen statutorily-created committees, councils, and commissions. The Superintendent is the executive head of the Department and works in partnership with the State Board on the development of regulations and policies governing P-12 public education. From the licensure of new educators to the adoption of academic content standards, the reporting of school performance, and the administration of federal and state appropriations, the Department, directly and indirectly, impacts the achievement of the nearly half a million school-aged children and some 30,000 adults seeking high school equivalency education. Pursuant to an Executive Order issued by Governor Sandoval in 2013, the Department also shares educational responsibility with the Nevada Department of Health and Human Services for an estimated 180,000 children aged 0 to 4. The Department works in close coordination with local school districts, the State Public Charter School Authority (SPCSA), the Nevada System of Higher Education, and Regional Professional Development Programs. Superintendent Ebert looks forward to convening with these key stakeholders to create the 2020 STIP. These partnerships will be leveraged in the 2020 STIP to maximize operations across all State Departments to ensure the brightest future for Nevada’s students.

## Department Goal

“Fastest Improving State in the Nation.”

The Department’s five-year Strategic Plan, DOE ESSA (Every Student Succeeds Act) submission, and now the annual STIP are in alignment as the catalyst for improvement and an opportunity to rally the state behind a singular goal: becoming the fastest improving state in the nation (FISN).  The below graphic shares the Department’s eight FISN indicators the Department’s progress toward becoming the Fastest Improving State in the Nation with a blue line reflective of the most recent school year:

## Fastest Improving State in the Nation Progress

The external alignment of our Strategic Plan, ESSA, and STIP set the agenda for our internal operations. The Objectives and Strategies outlined later in the 2019 STIP confirm that the Department completes nothing in isolation. All Objectives were approved by the Superintendent and Deputy Superintendents, and they received feedback from the Superintendent’s Cabinet and Objective Leads to confirm alignment to our FISN (Fastest Improving State in the Nation) Goals, State Board of Education goals, and FISN levers.

To secure Nevada’s place as the fastest improving state in the nation, the Department must continue to implement recently passed programs, hold itself accountable for improving student achievement, reinvest where success is realized, and redirect funds where outcomes are lagging.

While all of the Department’s FISN Goals experienced advancement, there are some notable successes experienced by students and teachers worthy of additional celebration.

Student Successes

- Nine Nevada Schools Earn First College Board AP Computer Science Female Diversity Awards for Female Representation

- Upwards of 50 adult learners completed high school degree and enrolled in college courses as part of Nevada-Accelerated Career Education (NV-ACE) Project.

- For the Class of 2018, 24.8% of students scored a 3 or higher on an AP Exam.

- Nevada students exceeded their annual FISN goal for CTE Completers by achieving 11,425 successful CTE Completers for 2019.

- Nevada high schools posted their highest graduation rate ever at 83.17 percent for the Class of 2018 – an increase of 2.32 percentage points.

- Nevada has 31 Shining Stars Schools that achieved 4 and 5-Star status while also serving a high percentage of students in poverty.

Educator Successes

- The number of National Board Certified Teachers in Nevada has nearly tripled in the last three years to 906 National Board Certified Teachers.

- Zoom, Victory, Read by Grade 3, Nevada Ready 21 Technology Grant, Social Workers in Schools, Great Teaching and Leading Fund, and the Turnaround Schools Grant are recommended for continued funding by ACS Ventures, an external evaluator.

- Children with Disabilities are enrolled in Inclusion Early Childhood Programs at a rate of 39.4% which is the highest in Nevada's history.

- Nevada has 58 4- and 5-star High Quality Pre-K centers, and surpassed the 2019 goal of 25 centers.

- 105 Schools in Nevada Improve Chronic Absentee Rate by At Least 10 Percent.

Legislative and Governor’s Recommended Budget Successes

- Assist all at-risk weight students in the lowest quartile - $139.8M

- Establish support for school safety - $76M

- First committee passage of SB 89: School Safety Task Force

- Expand CTE programs to align with Nevada industries- $27M

- Historic increase for preschool development - $57.7M

- Successful hearing of SB 84: Statewide Pre-k (declared exempt)

- Nearly double funding for Read by Grade 3 - $63.4M

- First committee passage of AB 289: Read by Grade 3

- Salary support for all school personnel - $356M

- Nearly double teacher supply reimbursement - $9M

## Members of the Nevada State Board of Education

Elaine Wynn, President

Mark Newburn, Vice President

Felicia Ortiz

Robert Blakely

Tamara Hudson

Dr. Katherine A. Dockweiler

Dawn Etcheverry Miller

Teri White

Cathy McAdoo

David Carter

Ashley Macias

# SECTION 1: DATA REVIEW AND ANALYSIS

The Department of Education collects and reports two primary sources of accountability data concerning the achievement of pupils: the Nevada Report Card (http://nevadareportcard.nv.gov/) and the Nevada School Performance Framework (NSPF). The Department also collects and reports data from the National Assessment of Educational Performance (NAEP), as well as information on Career and Technical Education (CTE) that is not included in the Nevada Report Card. Included below is a high-level review of these available data streams; Department employees and stakeholders analyzed this information for the reporting of problems and factors and the creation of related strategies.

## DEMOGRAPHICS OF NEVADA’S K-12 POPULATION

As of April 2019, there were 492,642 students enrolled in Nevada’s K-12 public schools (district and charter combined). Three entities -- Clark County School District, Washoe County School District, and the State Public Charter School Authority -- represent 89% of the total statewide enrollment, with the balance distributed among the 15 other districts.

### Ethnicity

Nevada has a rapidly changing student population. The fastest growing ethnic group is Hispanic, with a corresponding decrease in the percent of White students as illustrated in Figure 1. Nevada’s Hispanic population is also seeing a transfer of growth from a largely first-generation Hispanic population to now a largely second-generation Hispanic population.

Beginning in the 2010-2011 school year, a new ethnicity classification, “Two or More Races,” was introduced, which resulted in shifts in other categories. As revealed by data elsewhere in this analysis, long-standing ethnic subgroups (Black and American Indian in particular) continue to experience significant achievement gaps in student performance.

### Special Populations

The below graph for Special Populations Enrollment illustrates the three primary special population groups, English Learners (EL), Free/Reduced- Price Lunch (FRL), and Special Education (IEP) program. There is a significant increase in students qualifying for FRL, particularly since the 2009-2010 school year, and it reached an all-time high of 60% in 2016-2017. Interestingly, it appears that an increase in the percentage of students qualifying for FRL coincides with a marginal decrease in the percentage of students identified as EL.

## Equity

The Department could not declare its FISN Goal without recognizing and developing Objectives and Strategies to reconcile the significant achievement gaps between Nevada’s most vulnerable and underrepresented populations with the rest of the state. Nationwide, underrepresented students see gaps in achievement, oftentimes in the indicators highlighted by our FISN Goals: graduation, standardized testing, and access to high-quality services.

It is the priority of the Department to use the Data Analysis portion of the STIP to inform the Objectives and Strategies so that Nevada becomes the Fastest Improving State in the nation for all students. Nevada’s students have lagged behind their peers across the country on a variety of measures, from early childhood education enrollment to NAEP performance to high school graduation and college enrollment. The opportunity gap for students of color, students in poverty, students with disabilities, and ELs reveals a disproportionate impact on students. The $340 million infusion from the 2015 Legislative session initiated significant programs to ensure educational equity for all Nevada students. Governor Sisolak’s Recommended Budget as proposed for the 2019 Legislative Session includes a historic investment in Prekindergarten, the largest to-date investment in mental and behavioral health, an enhancement to nearly double the allocations to both SB 178 and Teacher Reimbursements, and the creation of the School Safety Budget Account.

### Evidence of the Equity Challenge

In the 2016-2017 Nevada School Performance Framework (NSPF) rating, Nevada’s school accountability system, one-fourth of schools rated received one- or two-star ratings on a five-star scale. A disproportional number of these low performing schools serve students that qualify for free and reduced lunch or are designated as English learners.

To date, NDE has employed a broad and shallow approach rather than a narrow and deep approach in struggling schools in creating new strategies, building partnerships, identifying effective leaders and teachers, and providing access and systems to manage data for school improvement. Historically, this has been due to a lack of aligned high-expectations for schools and student growth and a lack of a coherent framework for support.

To illustrate this for one of Nevada’s special populations, Black students make up approximately 11% of total enrollment, but only 4% of Nevada’s Advanced Diploma graduates, indicating an equity gap for Black students. The equity gap begins sooner than high school, with 1 out of every 4 Black students proficient on the 3rd Grade Smarter Balanced Mathematics assessment, compared to 1 out of every 2 Nevada students proficient on the 3rd Grade Smarter Balanced Mathematics.

### Current Nevada Efforts

Nevada is committed to developing a culture of improvement that provides each student with an opportunity to successfully participate as a productive citizen in a global economy. The culture of improvement requires districts, school leadership, staff members, and the community to have a strong commitment to school improvement and understand what it will take to improve outcomes.

### Accountability

The Nevada School Performance Framework (NSPF) was originally launched in 2012 and was redesigned through several stakeholder engagements that began in January 2015. The engagements included a broad base of community, business, and education professionals that were empowered to make recommendations regarding the indicators, measures, and weights for Nevada’s next school accountability system. Each year NDE publishes the NSPF to measure and communicate school effectiveness of all public schools, both traditional district and charter schools.

The revised NSPF school ratings were released in September 2017. The Elementary and Middle School NSPF rating incorporates measures of student proficiency, student growth, English language proficiency, closure of achievement gaps, and attendance as a measure of student engagement.

The High School NSPF rating is similar to the Elementary and Middle School NSPF rating but includes graduation rate and college and career readiness assessment results in lieu of student growth and closure of achievement gaps.

The NSPF also serves an important equity role through reports on student proficiency by various student populations: racial and ethnic subgroups, students with special education needs, students who are ELs, and students who are economically disadvantaged. At least ten students must be assessed to be included in these measures to ensure student anonymity. Additionally, Nevada established a new group of students in elementary and middle schools: “students in need of improvement.” This group included students who did not earn a passing score on the prior administration of the state test. Longitudinal data indicates that this group of students disproportionately consists of diverse students. The growth target of these students will be measured and displayed in what Nevada refers to as the closing achievement gaps indicator.

Schools are given a NSPF rating of one to five stars, with five-star schools signifying extraordinary performance and successfully preparing students for the global economy. These ratings are published on the NSPF webpage at NevadaReportCard.com. Using the NSPF, schools will be identified for specific recognition and support.  NDE works with districts to prioritize service and assistance to one- and two-star schools to improve student performance through a variety of supports and interventions.

### Federal School Support and Intervention

There are two main categories of schools that the Department identifies for support and improvement. The first category is Comprehensive Support and Improvement (CSI) Schools, which includes the lowest-performing five percent of schools in Nevada and high schools with graduation rates below 67%. The school district of the CSI school or the charter school is expected to write an annual School Performance Plan (SPP), which must address optimal resource distribution and how the school and/or district will address them. The local school leadership, the district, and the Department must approve the plan. Monitoring the school plan and prioritized support will be provided by NDE. It is the district or charter school’s responsibility to notify parents about why the school is a CSI school and how they can be involved in the improvement process.

CSI schools are also subject to more rigorous state and local action. They can be considered for State Turnaround designation and, to date, are considered for inclusion in the statewide Nevada Achievement School District (NV ASD). The NV ASD may accept up to six schools per year for transformation and pair those schools with high-quality school operators or transformation teams.

The second category is Targeted Support and Improvement (TSI) Schools, which remain under the purview of the district or charter school. This includes schools that have one or more persistently under-performing student groups. These schools are identified annually by NDE and monitored by the district or charter school through implementation of their SPP. When all quality indicators are met, the school can exit TSI status. If quality indicators are not met within three years, the school moves to CSI status.

### Success Indicators

The most important change that will happen in accountability is an increase in the number of three-, four-, and five-star schools across the state. Recognition of high performing schools, expansion, and replication of successful programs, and developing the talented individuals who make programs work are all strategies in NDE school improvement plans. Ultimately, school improvement and transparency in accountability will move to a system where parents and families can understand how schools are doing with students like theirs, and where schools are being held accountable for the delivery of a high-quality education.

### State Role

NDE will release the NSPF annually, which gives families and community members a transparent and comparable view into student achievement and academic growth, student engagement, and overall school success. NDE will provide differentiated support to low-performing schools, depending on the level of performance and services needed. As a part of that work, Nevada will use the analysis of equitable distribution of effective teachers to help support staffing and teacher professional development in low-performing schools. This will be done through collaboration with Regional Professional Development Providers  (RPDP), regional cooperatives that provide training and support to districts and charter schools.

The Department’s multi-tiered approach to differentiated school improvement identifies the roles and responsibilities for NDE, districts, and charter schools for each tier, in addition to parent actions, to facilitate system level alignment and coherence on accountability and supports.

Nevada will use this approach to prioritize its work and more effectively target resources, supports, and interventions. This will ensure that NDE, districts, and charter schools are aligned and responsive to specific school needs.

## STUDENT PERFORMANCE

### Assessments

The Nevada State Assessment System ensures all public school students, no matter where they attend school, receive a quality education. The figure below shows the distribution of all required assessments by grade in Nevada. Local schools and districts determine additional assessments not included in the graphic or the descriptions that follow.

*Non-universal assessments

All State assessments provide testing accommodations for students in special education and 504 programs.

Nevada State Assessment Descriptions:

Brigance: The Brigance is a collection of quick, reliable, and highly accurate early childhood education assessments and data-gathering tools that are nationally standardized. All students are required to be assessed upon entrance to Kindergarten to identify individual student needs and track progress, specifically regarding a student’s literacy level.

Measures of Academic Progress (MAP): Measures of Academic Progress (MAP) is a computer-adaptive assessment utilized to monitor student growth to inform and personalize instruction. MAP was officially adopted by the Nevada State Board of Education to assess Nevada students as a part of the Read by Grade Three (RBG3) program. With the implementation of MAP in school year 2017-18, Nevada will, for the first time, have aligned standards, professional development, assessments, and expectations in Kindergarten through Third Grade.

Smarter Balanced Assessments (SBAC): The Smarter Balanced assessments are a key part of monitoring student progress in grades 3-8 towards success in college and career. The computer-adaptive format and online administration of the assessments provide meaningful feedback that teachers and parents can use to help students succeed. The assessments are aligned with the NVACS in English Language Arts and Mathematics and allow Nevada to measure itself with 15 other states that also administer the Smarter Balanced assessment.

Nevada was the first Smarter Balanced Assessment Consortium member to pass federal Peer Review of State Assessment Systems that confirmed the State’s assessment in grade 3-8 in English Language Arts is aligned to the State’s academic content standards; is valid and reliable; provides student results in terms of the State’s student academic achievement standards; and provides clear information about student achievement.

Science: All public school students in grades 5, 8, and 10 must participate in the Science assessments. There is also an End of Course examination in science that students will need to pass to fulfill high school graduation requirements (starting with the graduating class of 2020). The Science assessments are a computer-based test administered at schools once a year in the spring. Spring 2017 is the first year that Nevada Science scores will report on student performance based on the newly adopted NVACSS. The Nevada State Board of Education and the Nevada Council on Academic Standards set achievement level cut scores during summer 2017.

College and Career Readiness Assessment, ACT: To be eligible for graduation, all students, free of charge, must participate in Nevada’s College and Career Readiness (CCR) assessment during their junior year of high school. The Nevada State Board of Education chose the ACT as its CCR assessment. A student’s ACT score will not be used to determine graduation eligibility but can be submitted with college applications. The ACT is a nationally recognized college admissions exam that is accepted by all four-year colleges and universities in the United States.

Nevada Alternate Assessment (NAA): The Nevada Alternate Assessment (NAA) is the state assessment for NVACS Connectors. The assessment is administered to less than 1% of all Nevada students who meet required eligibility criteria. The NAA assesses student academic performance on the NVACS Connectors. Currently, alternative forms of the NAA are being discussed to more effectively assess Nevada’s students with significant cognitive disabilities.

English Language Proficiency Assessment (WIDA): Students identified as Limited English Proficient (LEP) are annually assessed for English proficiency in the four domains of speaking, listening, reading, and writing. All English Learners are required to participate in the English Language Proficiency Assessment, commonly referred to as WIDA.

### Success Indicators

Closing the achievement gap on state assessments is a priority in Nevada. All Nevada students will have high expectations and rigorous standards in their K-12 education that will successfully prepare them for a global 21st century. The standards will provide educators a clear understanding of what is expected and will be used to provide standards-based instruction. Along the way, students will be assessed to track student progress and ensure students receive the appropriate interventions if proficiency is not met.

Overall, there was a positive trend in aggregate performance of Nevada students in math and reading during the previous four years according to NAEP, or the National Assessment on Educational Progress, which is one of the Department’s FISN Goals, as reflected in the above table comparing our NAEP scores from 2009 to most recently in 2017.

### Ethnicity

Overall performance of students appears to have improved over the past five years with a marginal decline in performance across all groups, except Asians, in 2013-2014. As illustrated in the earlier section on the Equity Challenge, a performance gap between ethnic groups exists. The Department recognizes that opportunity and achievement is not accessible to all of Nevada’s students, and the STIP is written to be corrective of such gaps students experience. It is worthwhile to note that, on the Department’s journey to becoming the Fastest Improving State in the Nation, Matthew Chingos of the Urban Institute in a 2017 NAEP (National Assessment on Education Progress) 4th grade reading study identified Nevada as a state that supports its students to achieve at higher rates when compared to other states and controlled for age, race, frequency of English spoken at home, special education status, free or reduced-price lunch eligibility, and English learner status.

### Special Populations

Data for the three primary special population groups; IEP, EL, and FRL are of a more complex nature. There exists a correlation between EL students and FRL students. This correlation, or covariance, between groups, means that an overlap exists between the two data sets. As such, a change in values for one group necessarily means a change in the other will exist, thus making an understanding of the factors affecting such changes more challenging. Select cohorts of public schools which serve dominantly EL and FRL communities are Zoom and Victory Schools, respectively.

### Career and Technical Education

The Nevada Office of Career Readiness, Adult Learning, and Education Options (CRALEO) serves a breadth of students who are focused on more technical academic experiences as they grow into individuals who are college and career ready. A variety of performance indicators are available to review CTE student performance. Beyond providing a means of monitoring success, the data have the potential to provide insight into some of the motivation and drive that results in students taking CTE coursework. During the 2016-2017 school year, all grade levels experienced decreased enrollment in CTE programs with an overall decrease enrollment in CTE enrollment of approximately 3 percent from 2015-2016 (63,294) to 2016-2017 (61,448). Eleventh grade experienced the most significant decrease;  10th grade experienced a slight increase at 2 percent.  Preliminary data for 2017-2018 indicates an overall increase in CTE enrollment of approximately 4 percent (61,448 to 63,855). The second significant trend is higher graduation rates for CTE students compared to their state peers from the past four years, as evidenced in the below graph.

### Graduation Rates

Beginning in the 2011-2012 academic year, a new formula was used in the calculation of graduation rates. The designation is “Adjusted Cohort Graduation Rate.” Overall, the statewide graduation rate has increased steadily over the past four years, and it is considered fourth in the nation for growth, behind Alabama, Georgia, and the District of Columbia, according to a 2016 report from The White House. Nevada kept a robust pace of high school graduation rate growth by exceeding our FISN Graduation Rate goal for the class of 2017 with a cohort graduation rate of 81% and again in 2018 with a graduation rate of 83%. The below graph shows the cohort graduation rate disaggregated by ethnicity as well as the statewide total through the class of 2018.

### Disciplinary Incidents

Historically the Department of Education has tracked six categories of discipline incidents:

- Violence to Other Students

- Violence to School Staff

- Possession of Weapons

- Distribution of Controlled Substances

- Possession of Use or Controlled Substances

- Possession of Use of Alcoholic Beverage

During the 2011-2012 school year, a seventh factor, Bullying, Cyber Bullying, Harassment & Intimidation, was added. As of the 2013–2014 school year, harassment and intimidation were no longer identified as violations of a Safe and Respectful Learning Environment; the definitions of these two incidents were combined under the definitions of Bullying and Cyber-Bullying. The below graph illustrates the initial spike in reported bullying data due to the reporting process being introduced and a tapering off of bullying incidences in 2016-2017 after supports were put in place.

## FISCAL INFORMATION

Student instruction costs just under 60% of each dollar of per-pupil education expenditure, a figure which has risen very gradually for the fifth year in a row, following a spike seven years ago. Leadership spending per pupil has risen from a nearly constant long-term level of about 7.5% to 8.3%.

## TEACHER AND CLASSROOM DATA

In accordance with Nevada’s federal “Every Student Succeeds Act” (ESSA) Plan, NDE is required to ensure that students from low-income families and students of color are not taught at higher rates than other students by inexperienced, unqualified, or out-of-field teachers. Nevada is committed to ensuring that all students, particularly those in identified subgroups, have access to effective teachers and school leaders.

During the implementation of the statewide Nevada Educator Performance Framework (NEPF) for the 2017-2018 school year, districts reported that less than 2% of teachers received an Ineffective or Developing Rating. In contrast, nearly 85% of teachers each year received an Effective rating with approximately 13% of teachers receiving a Highly Effective rating.

### 2017-2018 NEPF Ratings as Reported by Districts

| LEA (schools) | INEFFECTIVE | MINIMALLY EFFECTIVE | EFFECTIVE | HIGHLY EFFECTIVE | Summative Ratings |
| --- | --- | --- | --- | --- | --- |
| Carson City (11) | 0.0% | 5.5% | 71.6% | 22.9% | 380 |
| Churchill (6) | 0.0% | 3.4% | 79.8% | 16.9% | 178 |
| Clark (349) | 0.1% | 0.9% | 90.3% | 8.6% | 15342 |
| Douglas (13) | 0.0% | 1.6% | 77.6% | 20.7% | 304 |
| Elko (28) | 0.0% | 0.8% | 69.3% | 29.9% | 361 |
| Eureka (3) | 0.0% | 0.0% | 47.8% | 52.2% | 23 |
| Humboldt (11) | 0.0% | 3.2% | 81.4% | 15.4% | 188 |
| Lander (4) | 0.0% | 2.1% | 91.7% | 6.3% | 48 |
| Lincoln (9) | 0.0% | 1.1% | 77.6% | 21.2% | 85 |
| Lyon (18) | 0.0% | 2.2% | 65.4% | 32.4% | 410 |
| Mineral (2) | 0.0% | 8.0% | 80.0% | 12.0% | 25 |
| Nye (24) | 0.4% | 4.3% | 90.2% | 5.1% | 276 |
| Pershing (4) | 0.0% | 0.0% | 96.0% | 4.0% | 50 |
| Storey (4) | 0.0% | 0.0% | 56.3% | 43.8% | 16 |
| Washoe (96) | 0.0% | 1.3% | 62.4% | 36.1% | 2342 |
| White Pine (8) | 1.3% | 4.1% | 78.1% | 16.4% | 73 |
| STATEWIDE % (590) | 0.1% | 1.2% | 85.4% | 13.2% |  |
| STATEWIDE # of Teachers | 25 | 242 | 17060 | 2640 | 19967 |

The high number of teacher vacancies during the past three school years is of particular concern. While overall improvements have been made since the 2015-2016 school year, there were still 715 vacancies statewide as of November 2017. Additionally, there is still an inequitable distribution of high teacher vacancies in 1- and 2-star schools as well as in Victory and Zoom Schools, which serve students in our highest poverty zip codes, and highest concentrations of English Language Learner populations, respectively.

### 17-18 Teacher Vacancies as Reported by Districts as of November 2017

|  | 2016-2017 Total Staffing | 2016-2017 Total Vacancies | % Vacant Nov 2017 | % Vacant Nov 2016 | % Vacant Dec 2015 |
| --- | --- | --- | --- | --- | --- |
| Statewide | 22,598.9 | 715.8 | 3.2% | 2.5% | 4% |
| Victory | 1,269.7 | 68.0 | 5.4% | 4.0% | 9% |
| Zoom | 2,618.0 | 82.0 | 3.1% | 3.3% | 6% |
| 1-Star | 548.3 | 26.0 | 4.7% | 4.8% | 7% |
| 2-Star | 4,629.5 | 240.8 | 5.2% | 4.5% | 7% |
| 3-Star | 9,841.8 | 290.5 | 3.0% | 2.0% | 4% |
| 4-Star | 3,694.2 | 64.5 | 1.7% | 1.7% | 2% |
| 5-Star | 3,022.3 | 37.0 | 1.2% | 1.3% | 1% |
| Washoe | 3,850.1 | 61.0 | 1.6% | 1.0% | 1% |
| Clark | 15,725.0 | 534.0 | 3.4% | 2.8% | 4% |
| Other Districts | 3,023.8 | 120.8 | 4.0% | 3.6% | 3% |

## FAMILY ENGAGEMENT DATA

New initiatives and a comprehensive reform plan are a great engagement opportunity for families. With information available about new programs, teachers and school leaders will partner with families to identify local programs and how to get access to these new programs.

The Department monitors School Performance Plans (SPPs) for the inclusion of effective family engagement practices and strategies. The inclusion of such strategies in an SPP is expected to increase student achievement. The below pie chart  shows the total number of oberserved family engagement standards in 2017-2018 Rising Star Schools SPPs:

SECTION 2: COMMON PROBLEMS AND FACTORS

State law requires this plan to include the “identification of any problems or factors common among the school districts or charter schools in this State, as revealed by the review and analysis” of certain data (outlined in Section 1 above). The Department has identified eight problems and factor areas that are readily apparent in the most recent educator and student and school performance data:

- Student performance in reading;

- Student performance in mathematics (specifically in middle school);

- Student performance at the middle school level;

- Achievement gaps between student subgroups;

- Early childhood preparation; and

- College and Career Readiness

- Equitable Distribution of Effective Educators

- Support and Respect for Educators

In addition, conversations between Department staff and stakeholders led to the identification of three key levers for improving Nevada’s student achievement. The three key levers are:

- Identifying and improving the state’s lowest performing schools;

- Developing and supporting great school leaders; and

- Making data informed policy and instructional decisions.

Presented in Section 3 are the objectives and strategies for improvement in each of these identified problem/factor areas, the assignment of Department personnel, measurement criteria, and associated timelines. Several “cross-cutting” strategies are also presented.

# SECTION 3: GOALS, OBJECTIVES, TIMELINE, AND STRATEGIES FOR IMPROVEMENT

The Department engaged stakeholders in preparation for the development and submission of its Every Student Succeeds Act Plan and Five-Year Strategic Plan, adopted by the State Board of Education in December of 2016. Department staff analyzed data to identify critical Strategies within and across offices which would result in increased student achievement and educator effectiveness. This process resulted in the following Objectives nested under each goal which defines the focus for offices within the Department. Alignment of day-to-day work by Department staff and the Mission and Vision in the STIP is evident in the following Goals, Objectives, Strategies, Metrics, and their Annual Targets. Each office, in consultation with leadership, is tasked with identifying Deliverables that should result in meeting the Annual Targets listed below, which align to the Common Problems identified within the Data Analysis of the STIP. The presentation of the Goals and Objectives below contemplate a future review of the Strategic Plan given that many of the timelines, by their nature, extend beyond the “annual” nature of this particular plan.

Through the Department’s stakeholder engagement during the course of its Every Student Succeeds Act, the Department developed, and the State Board adopted, a goal to become the Fastest Improving State in the Nation. The below nationally-comparable Goals and Annual Targets depict the current state of student achievement and progress needed to exceed the state which held the fastest improvement on that particular measure over the previous five-year period. The table that follows is an outline of the Five-year-Strategic Plan with state-facing Goals adopted by the State Board in December 2016.

Early Childhood Program Quality Long-term Goals and Annual Benchmarks

| Goal | 4 or 5 Star Rating | Annual Targets | Interim 4 or 5 Star Rating Goal | Long-term 4 or 5 Star Rating Goal |
| --- | --- | --- | --- | --- |
| The fastest improving state for increasing the number of 4- and 5- star early childhood programs. | 2015-2016 12 | 2016-2017 15 2017-2018 20 2018-2019 25 | 2019-2020 30 | 2021-2022 40 |

Special Education Inclusion in Early Childhood Programs Long-term Goals and Annual Benchmarks

| …..Goal | Baseline Percent Inclusion | Annual Targets | Interim Inclusion Goal | Long-term Inclusion Goal |
| --- | --- | --- | --- | --- |
| The fastest improving state for including children with disabilities in inclusive early childhood programs. | 2015-2016 30.2% | 2016-2017 33% 2017-2018 40% 2018-2019 50% | 2019-2020 60% | 2021-2022 75% |

English Language Proficiency Long-term Goals and Annual Benchmarks*

| Goal | Baseline Score | Annual Targets | Interim Score Goal | Long-term Score Goal: |
| --- | --- | --- | --- | --- |
| The fastest improving state on the English Language Proficiency Exam. | 2015-2016 24.9% | 2016-2017 25% 2017-2018 38% 2018-2019 51% | 2019-2020 64% | 2021-2022 95% |

*90% of ELs will exit EL status within six years of initial EL identification and 90% of Long-term ELs will exit EL status by 2022. This will be measured by aggregating the number of ELs who achieve Nevada’s EL exit criteria over a six-year period.

Smarter Balanced Assessments Long-term Goals and Annual Benchmarks

| Goal | Proficient | Annual ELA Targets | Annual Math Targets | Interim Proficient Goal | Long-term Proficient Goal |
| --- | --- | --- | --- | --- | --- |
| The fastest improving state for increasing student achievement on Smarter Balanced assessments. | 2015-2016 ELA 48% 2015-2016 Math 34% | 2016-2017 51% 2017-2018 54% 2018-2019 57% | 2016-2017 36% 2017-2018 37% 2018-2019 38% | 2019-2020 ELA 59% Math 39% | 2021-2022 ELA 61% Math 41% |

High School Graduation Long-term Goals and Annual Benchmarks

| Goal | Class of 2015 | Annual Targets | Interim Graduation Rate Goal | Long-term Graduation Rate Goal |
| --- | --- | --- | --- | --- |
| The fastest improving state for increasing high school graduation rates. | 70.77% | 2016-2017 73% 2017-2018 75% 2018-2019 77% | 2019-2020 80% | 2021-2022 84% |

ACT Long-term Goals and Annual Benchmarks

| Goal | Baseline Composite Score | Annual Targets | Interim Graduation Rate Goal | Long-term Graduation Rate Goal |
| --- | --- | --- | --- | --- |
| The fastest improving state for increasing ACT benchmark scores. | 2015-2016 17.4 | 2016-2017 17.9 2017-2018 18.1 2018-2019 18.3 | 2019-2020 18.5 | 2021-2022 20 |

NAEP Proficiency Long-term Goals and Annual Benchmarks

| Goals | Baseline Score 2015 | Annual Targets 2017 | Annual Targets 2019 | Interim NAEP Score Goal: 2021 | Long-term NAEP Score Goal: 2023 |
| --- | --- | --- | --- | --- | --- |
| . . . . The fastest improving state for NAEP proficiency. | Grade 4 Science 142 Writing 145 Reading 214 Math 234 Grade 8 Science 149 Writing 143 Reading 259 Math 275 | Grade 4 Science 143 Writing 147 Reading 216 Math 236 Grade 8 Science 150 Writing 145 Reading 261 Math 277 | Grade 4 Science 145 Writing 149 Reading 218 Math 238 Grade 8 Science 151 Writing 147 Reading 262 Math 279 | Grade 4 Science 147 Writing 151 Reading 220 Math 240 Grade 8 Science 152 Writing 149 Reading 264 Math 281 | Grade 4 Science 149 Writing 153 Reading 222 Math 242 Grade 8 Science 153 Writing 151 Reading 266 Math 283 |

## Objective 1 – Strong Start

Quality early childhood (Birth – 3rd Grade) environments that include the establishment of an effective system of early literacy instruction and intervention as the key to developing the solid groundwork for learning – one that ensures equal access to future success for all Nevada children.

- Strategy 1.1: Improve the quality of early childhood (Birth – 3rd grade) programs.

- Strategy 1.2: Increase access to high-quality early childhood programs.

- Strategy 1.3: Establish an aligned system of screening and assessment across early childhood programs (Brigance, MAP, Smarter Balanced 3rd Grade, and Read by Grade 3).

- Strategy 1.4: Improve effective literacy instruction for both emergent skills and the domains of literacy.

| Metrics | Baseline Data (SY 2015-16) | Five-Year Goal (SY 2020-21) | Annual Progress |
| --- | --- | --- | --- |
| - Number of seats in 4 -and 5-star Quality Rating & Improvement System (QRIS) programs - Number of 4- and 5-star QRIS programs | - 1167 seats (3.7% of state total) - 12 programs (4% of state total) | - 3500 seats (11% of state total) - 30 programs (10% of state total) | - 3957 seats in 4- and 5-star rated programs. - 58 Total -38 4-star and 20 5-star rated programs (31% of 189 rated programs) |
| - Number of children who are receiving child care subsidies (at or below 130% Federal poverty level) enrolled in a 4- or 5-star rated program | - Four children receiving subsidies in 4- and 5-star rated programs (.04% of total eligible) | - 875 children receiving subsidies in 4- and 5-star rated programs (12% of total eligible) | - 58 Total -38 4-star and 20 5-star rated programs (31% of 189 rated programs) |
| - Number of children ages 3-5 with IEPs who are attending a regular early childhood program and receive the majority of special education and related services in the regular early childhood program | - 30.2% (2015 Annual Performance Report Indicator 6a data) | - Increase to 60% | - Currently 39.4% of children ages 3-5 with disabilities are being served in regular education settings. |
| - Increase the number of students ready based on the Kindergarten Entry Assessment | - Baseline data to be collected 2017-2018 school year | - 5-year goal to be created after 2017-2018 school year | - Annual goals to be set after baseline data is collected |
| - Increase the number of students who are proficient in reading as measured by the Measures of Academic Progress (MAP) reading assessment | - Baseline data to be collected 2017-2018 school year | - All 3rd grade students performing at 60th percentile or higher by 2021. | - Annual goals to be set after baseline data is collected |

Objective 2 – High-quality Standards, Curriculum, Instruction, & Support

Standards-based instruction encompasses the critical elements of content, students, and teachers which make up the Instructional Core and is necessary to ensure all students actively engage with and ultimately master the Nevada Academic Content Standards (NVACS). Every school district in Nevada will have a knowledgeable and cohesive leadership team that guides the professional learning and practice in alignment with NEPF standards, indicators, and protocols of all administrators, teachers, and staff so that every student experiences highly effective teaching and instructional leadership, as defined by learning, and assessment practices in every classroom, every day.

- Strategy 2.1: Maintain high-quality content standards and identify and support instruction of high-yield ELA and Mathematics standards.

- Strategy 2.2: Develop and curate state-approved, evidenced-based instructional material database and build capacity of educators to use evidence-based instructional materials.

- Strategy 2.3: Build capacity of school leaders to identify and support high-quality instruction aligned to standards and curriculum.

| Metrics | Baseline Data (SY 2017-18) | Five-Year Goal (SY 2020-21) | Annual Progress |
| --- | --- | --- | --- |

| - Annual review to identify high-yield instructional targets - Annual review to determine if targeted instructional support is closing gaps - Smarter Balanced Mathematics FISN targets met - Align Professional Development (PD) organizations to support targeted development efforts (workplans) | - Identify instructional priorities in the 2017-2018 school year and create instructional plan to close gaps and align Professional Development organizations for targeted support for 4-6% increase year over year | - All students demonstrate increased proficiency levels of at least 61% in ELA and 41% in Mathematics by 2021 - RPDPs and other state PD providers use annual Smarter Balanced analysis to target PD their efforts | - Identified high-yield instructional standards in 5th-8th grade Mathematics to improve Smarter Balanced performance |
| --- | --- | --- | --- |

Utilize Smarter Target tool to identify and support high-yield standards instructional efforts.

Maintain and Update high-quality NVACS

| - Develop and maintain high-quality content standards through 2021 that accounts for standards in need of updating and new standards proscribed by the legislature |  Implemented plan for completing Computer Science, Health, Social Studies, and Fine Arts. | - 2018-2019 Computer Science and Multi-Cultural - 2019-2020 Fine Arts, Social Studies & Science - 2020-2021 Health and Ed Tech | - Presentations at NASS, RPDP, and Curriculum Directors’ Meetings to communicate standards |
| --- | --- | --- | --- |

| ………Metrics | Baseline Data (SY 2017-18) | Five-Year Goal (SY 2020-21) | Annual Progress |
| --- | --- | --- | --- |

| - Conduct baseline audit and then annual review of schools to determine of Nevada schools are using high-quality, evidence-based materials (HQEB) - Increase number of schools using HQEB materials by 15% year over year - Support CSI & TSI schools to identify and increase HQEB materials by 15% year over year | - Baseline data to be collected 2017-2018 school year by auditing SPPs for HQEB materials | - 15% increase year over year will allow Nevada to surpass the fastest improving state with 80% of school with HQEB materials - 100% of 1003(a) Grant funds spent on evidence-based interventions meeting ESSA Evidence Levels 1-3 | - Used STIP planning sessions to collaborate between offices and create Objective Plan for alignment of SPPs to evidence-based, high-quality materials - Cross office review of SPPs for all CSI schools and NDE debrief with districts |
| --- | --- | --- | --- |

Audit School Performance Plans for use of evidence-based, high-quality materials and evidence-based interventions.

Support educators, schools, and districts to identify and implement the HQEB  instructional materials which work best.

| - Develop annual cycle with Nevada Ready network, RPDPs, etc., to match HQEB materials to high-yield standards - Support CSI & TSI schools to identify and increase HQEB materials by 15% year over year |  Utilize Nevada Ready Network to begin with resources that will address Middle School Mathematics high-yield standards - Through audit, identify how many CSI and TSI schools are not using HQEB materials | - All high-yield targets have corresponding HQEB materials and alignment to Instructional Materials Resource Center (IMRC) - All CSI and TSI schools are using HQEB materials | - Identified Middle School Mathematics high-yield standards and created a committee to supply aligned resources to teachers - OSIS supports CSI and TSI schools to select HQEB materials |
| --- | --- | --- | --- |

Develop and curate state-approved, HQEB instructional material database

| - ELA and Mathematics Core and Supplemental materials updated in 2018 - All 8 core standards updated by 2021 |  Instructional material database which only lists core materials and does not include information about evidence of effect size | - Fully built database with all 8 core content, standards, and information about evidence and effect size | - By the end of 2018, both ELA and Mathematics Core and Supplemental materials will be updated |
| --- | --- | --- | --- |
| - SLG scores, SBAC/NSPF growth data, and NEPF Implementation Monitoring Data | - Baseline to be determined using 16-17 SLG scores (10% NEPF overall) in comparison to SBAC growth from 15-16 to 16-17 | - Increase the percentage of schools with SLG scores aligned to SBAC/NSPF growth data | - Initial baseline data determined May 2018, second data set November 2018 using 18 SLGs and SBAC growth from baseline |

## Objective 3 – Annual Administration of Aligned Assessment & Accountability System

To meet the needs of students and teachers as well as federal requirements, Nevada has created a valid and reliable state assessment system aligned to NVACS. The Nevada Assessment System will inform the trajectory of areas such as with reading proficiency from pre-K through grade three and later in ELA, Mathematics, and Science in middle and in high school. This data reflects progress towards college and career readiness.

- Strategy 3.1: Administer valid and reliable assessments that are aligned with the academic content standards and/or state priorities: Brigance, MAP, Smarter Balanced, Science, ACT, NAA, EOC writing, and WIDA.

- Strategy 3.2: Publish and communicate assessment and accountability data to all internal and external stakeholders on all matters related to the statewide assessment system including but not limited to: NSPF, NEPF, NAEP, NevadaReportCard.com, graduation rates etc.

- Strategy 3.3: Maintain statewide data systems.

| …………Metrics | Baseline Data (SY 2015-16) | Five-Year Goal (2020-21) | ………..Annual Progress |
| --- | --- | --- | --- |
| - All assessments submitted for Federal Peer Review by 7/1/2019 - Reduce security incidents by 7% per year/24 incidents per year | - Continue test development to meet federal requirements and best practices - In 2017 state administration, there were 369 security incidents | - Continue test development to meet federal requirements - Between now and 2021, reduce security incidents by 123 incidents, or 33% | - All assessments submitted for Federal Peer Review by 7/1/2019 per USDOE - Decreased test administration security incidents each year by 24 incidents or 7% |
| - Complete on-time annual calendar of deliverables - Provide data to LEAs, NDE staff, and PIO in a manner understandable to each audience in advance of “public” release | - Finalize calendar of deliverables by 10/1 - Met department communication needs and all reporting requirements as per federal and state law | - Met all scheduled deliverables - Develop communication tools for the widest variety of audiences that facilitate an understanding of Department data; its application by diverse audiences, and best practices in data analysis | - Annual assessment windows and data delivery schedule met and communicated to all stakeholders - Meet delivery data and delivery requirements for Department release of and communication about data |
| - Increased Department awareness of the Data Collaborative mission and functional group participation in all Data Collaborative meetings - On schedule delivery of Infinite Campus enhancements and maintaince upgrades as determined by Infinite Campus Governance Board - Longitudinal Data System – meet project milestones and goals - Increase LEA satisfaction with vendor customer service | - Held 6 data collaborative meetings in 2017-2018 (2/22/18, 1/25/18, 9/14/17, 8/10/17, 7/13/17, 5/11/17) - Held 9 Governing Board meetings establishing goals, priorities, and schedule - Incorporated nPower schedule and deliverables into IT schedule - Create 2018 survey | - Thirty data collaborative meetings (6 annually) - Forty-five Governing Board meetings (9 annually) - Meet all established nPower project goals - Create Annual and 5-year Goal for increasing LEA satisfaction with vendor customer service year over year through 2021 | - Hold 6 data collaborative meetings - Hold 6 IC Governing Board meetings - Meet all established nPower project goals - LEA Customer service survey taken annually |

## Objective 4 – Data-informed Continuous Improvement

Data is best utilized when successfully interpreted by stakeholders to make decisions which create continuous improvement for student achievement. Utilizing the Assessment, Data, and Accountability Management (ADAM) office to serve as ADAM Liaisons paired with NDE programs will ensure data is interpreted without error and programming decisions reflect the Levers articulated at the beginning of the STIP: supporting lowest-performing schools, developing and retaining school leaders, and making data-driven decisions.

- Strategy 4.1: Provide analytic support and actionable data to internal and external stakeholders and assist in the interpretation of the accountability model and data.

- Strategy 4.2: Create and disseminate communications designed for the unique needs of stakeholders relating to all statewide assessments and the accountability system.

- Strategy 4.3: ADAM supports program staff to make data-informed decisions for continuous improvement.

| ……Metrics | Baseline Data (SY 2016-17) | Five-Year Goal (SY2020-21) | Annual Progress |
| --- | --- | --- | --- |
| - Activate and fulfill external and internal data analysis requests to support education programming in a timely manner | - During the baseline year of 2016-2017, the system was comprised of disconnected reporting sites (NSPF, Nevada Report Card, QRIS, NEPF, Infinite Campus, etc.) - Met delivery dates | - Increased coordination of reporting sites will support education programming explanation to make data-informed decisions to impact student achievement - Meet delivery dates | - Establish schedule for annual releases - Meet all delivery dates |
| - Create assessment and accountability communications that are easily interpreted by internal and external stakeholders | - 5 Assessment Content Reviews in 3 content areas for 7 grade levels - 2 Standard Settings - 10-15 District Test Director meeting - Regional training on assessment platforms - ADAM assessment conference - 14 stakeholder engagements accountability | - Complete stakeholder understanding of every aspect of the Nevada state assessment system. - Complete stakeholder understanding of every aspect of the Nevada state accountability system. | - LEA assessment awareness surveys - LEA accountability awareness surveys |
| - ADAM collaboration with Education Programs to increase data-informed decisions across NDE | - Created ADAM data support and Education Program expectations and assignments | - Internal stakeholders use data for each programming decision linked to improved student outcomes | - Identified ADAM data support for Education Programs Spring 2018 - ADAM data support and Programs meet as per program schedule |

## Objective 5 – 3-Stars in 3 Years

Nevada will create systemic improvements in the lowest-performing schools by supporting their implementation of improvement strategies with evidence- and research-based interventions. All schools currently identified as 1- and 2-star schools will be at least 3-stars in three years (on a 1-5 rating scale). Schools that have not yet reached 5-stars, must have a plan to get there. The Department has a moral and statutory obligation to ensure that schools in all zip codes are performing at the highest levels for students across the state.

- Strategy 5.1: Utilize a framework for an aligned school improvement approach to inform school and LEA needs assessment, planning, evaluation, funding, and interventions.

- Strategy 5.2: Implement state strategies to address chronic underperformance through available mechanisms (e.g., NDE Performance Compact, SB 92, and the NV ASD).

- Strategy 5.3: Support and develop the capacity of school leaders and utilization of data-informed instruction as two key levers to change schools’ outcomes and close opportunity gaps.

| Metrics 5.4: Implement SEA-LEA continuous improvement cycle. ………… Metrics | Baseline Data (SY 2017-18) | Five-Year Goal ( SY 2020-21) | …Annual Progress |
| --- | --- | --- | --- |
| - Statewide usage of post-ESSA needs assessment, School Performance Plan, District Performance Plan, and consolidated monitoring tools - Strategic alignment across post-ESSA tools to support schools (needs assessment, School Performance Plan, funding application, District Performance Plan, and consolidated monitoring tools) | - New needs assessment created for baseline in 2017-2018 | - In 2021, alignment piece across post-ESSA tools is completed - 100% of schools using newly redesigned needs assessment in 2020 | - Redesigned needs assessment, School Performance Plan, and District Performance Plan - Launched multi-grant application and continuation option - Setup recurring meetings for Tools for Schools and increased collaboration across NDE - Workgroup sessions with NDE and district leaders to redesign tools - Online intergrated platform - Desktop monitoring tool - Review and approve School Performance Plans for CSI schools |
| - Increase percentage of schools using evidence-based strategies to address data informed instruction and school leader development with a focus on CSI and TSI schools and districts - Effective and efficient use of funds | - All CSI schools that won federal 1003(a) grant are using an evidenced-based strategy in 2018 - TSI schools will be identified in 2018 | - All CSI and TSI schools using evidenced-based strategies | - 100% of 1003(a) Grant, Turnaround Grant, College and Career Readiness Grant, and RBG3 Grant chose evidenced-based interventions and strategies - NDE Evidence and Equity Convening - Strategic alignment of grants management process between the state, districts, and school - National recognition for OSSS school improvement work around evidence-based interventions - Competitive grant application redesigned for strategic allocation of evidence-based strategies |
| - Percentage of schools with state strategies that improved with an increasing index score | - Have an index score for elementary, middle, and high schools (high schools September 2018) - Will be able to calculate growth for elementary and middle in fall 2018 | - 3 Stars in 3 Years | - Built out state processes and tools for strategies - Rigorous CSI and TSI research-practice- partnership to identify and adopt key pillars for school turnaround - Build local capacity and evidence base through rigorous evaluations - Expansion of evidence-based interventions - CSI and TSI Guidance released and training across the state - NDE Data road shows across the state - State Title I, II, and III Directors Meeting |
| - Number of schools that meet the Rising Stars (previously underperforming schools list) criteria and are 3-star schools | - 157 1- and 2-star schools from the 2013-2014 rating system | - Reduce the number of 1- and 2-star schools by 30% | - NSPF Star Rating increased for 16 Zoom and Victory schools - Multi-tiered system of support for schools |
| - Schools that increase by 1-star ranking per year - Schools that persist at a 5-star rating | - 109 schools increased star rating from 2012-2013 to 2013-2014 - 99 5-star schools | - 99 5-star schools persist at the rating - 50 schools become 5-stars - 150 schools move at least one rating | - Baseline for schools under new ESSA NSPF released for elementary and middle in September 2017. - Strategic school partnerships and collaboration to spread evidence-based practices |

## Objective 6 – College and Career Readiness

By 2020, 65 percent of all jobs—compared to 28 percent in 1973—will require some form of postsecondary education, according to a new report from the Georgetown University Center on Education and the Workforce. At the other end of the education spectrum, the percentage of jobs requiring a high school diploma or less will continue to shrink. According to the report, Recovery: Job Growth and Education Requirements Through 2020, 72 percent of jobs were open to high school graduates in 1973; by 2020, that percentage is expected to fall to just 36 percent.

- Strategy 6.1: Use funding, law, and regulation to increase the number of students that meet post-secondary success.

- Strategy 6.2: Ensure equitable access to advanced coursework, dual enrollment, and work-based learning experiences for historically underserved student populations.

| …….Metrics | Baseline Data (SY 2015-16) | Five-Year Goal (SY 2020-21) | ……Annual Progress |
| --- | --- | --- | --- |
| - Increase number of CTE completers | - 7,559 CTE program completers | - 11,000 CTE program completers | - Exceeded annual FISN target of 9,279 CTE Completers by achieving 11,425 validated CTE Completers in 2018-2019 |
| - Increase the number of CTE concentrators (students who enroll in level 2 CTE courses) | - 12,595 CTE concentrators (enrolled in level 2 courses) | - 18,300 CTE concentrators (enrolled in level 2 courses) | - Exceeded goal of 18,300 CTE concentrators; 20,723 validated CTE Concentrators fin 2018-2019 |
| - Increase the number of students who enter college with college credit via dual enrollment, AP, or IB |  18,094 (May 2016) students who took AP exams - 2015 Legislature approved $8 million to expand dual enrollment programs and STEM grants - 5,140 students who scored three or higher on at least one AP exam | - 19,487 students who took AP exams (7.7% increase; n=464 additional students, per year) - 5,536 students who scored three or higher on at least one AP exam (7.7% increase; n=132 additional students per year) | - AP class participation up by 14% overall and in 2017 with a 10% increase in Exam scores of 3,4,5 - 36% increase in AP classes taken by Hispanic students & a 16% increase in Exam scores of 3,4,5 |

## Objective 7 – Educator Readiness and Equitable Distribution

- Strategy 7.1: Strengthen in-state educator preparation programs.

- Strategy 7.2: Reduce licensure barriers and maintain meaningful measures for full-state certification.

- Strategy 7.3: Identify and address educator equity gaps for all students.

- Strategy 7.4: Build capacity of educator preparation programs and school districts to implement a statewide code of educator ethics and conduct.

| …Metrics | Baseline Data(SY 2017-18) | Five-Year Goal (SY 2020-21) | ….Annual Progress |
| --- | --- | --- | --- |
| - Number of program completers and effective teachers hired and retained (particularly in diverse, high-needs schools) - Program complete and supervisor survey results - Praxis exam scores and other performance assessment pass rates | - Baseline data from newly-developed review, approval, evaluation, and accountability system to be collected during 2017-2018 school year | - Increase number from the baseline of in-state, high-performing educator preparation programs | - Building out data portal and surveys |
| - Number of provisional licenses issued - Percentage of provisional licenses (in-state and out-of-state) converted to standard or professional | - 2017-2018 baseline data to be collected from new OPAL system | - Decrease number of provisional licenses issued and increase percentage of provisional licenses (in-state and out-of-state) converted to standard or professional | - OPAL back-end launch in February 2018 |
| - Educator equity gap analysis (for students identified as high-poverty, minority, and/or EL) of effective, experienced, and fully certified teachers | - 2017-2018 Educator Equity Plan used as baseline data to be collected using 2016-2017 teacher experience, certification, and effectiveness measures | - Improvement targets will be set when baseline data is available | - Ongoing data collection and analysis to form 2017-2018 baseline and collaboration between department offices to analyze data |
| - Reduction in incidents of educator misconduct (arrests/convictions/corporal punishment, etc.) | - Baseline to be collected in 2017-2018 | - Goal will be set once baseline is collected for 2017-2018 | - Collaboration with department offices to collect baseline and determine annual and 5-year goals |

## Objective 8 – Family Engagement

Students benefit when their parents and family members are engaged in their education. The Department knows families are capable of playing a key role in their children’s education by supporting learning at home, advocating for all children, and making decisions to ensure students’ best interests are being taken into consideration when creating policies. The Department also believes it is the responsibility of the district and school staff to engage their families but equally important for the Department to support in building their capacity to do so.

- Strategy 8.1: Support district and school use of family engagement best practices.

- Strategy 8.2: Building educator capacity.

- Strategy 8.3: Empowering families.

| Metrics | Baseline Data (SY 2016-2018) | Five-Year Goal (SY 2020-2021) | Annual Progress |
| --- | --- | --- | --- |
| Nevada Policy on Parental Involvement and Family Engagement standards observed in School Performance Plans | Based on the observation of School Performance Plans, 12% of all Rising Stars schools (SY 2015-2016) are utilizing effective strategies in each of the six standards in the Nevada Policy on Parental Involvement and Family Engagement | By July 2021, based on the observation of School Performance Plans, 100% of all Rising Stars schools will utilize effective strategies in each of the six standards in the Nevada Policy on Parental Involvement and Family Engagement: - SY 16-17  42.3% - SY 17-18  52.42% - SY 18-19  65.04% - SY 19-20  80.65% - SY 20-21  100% | Based on the observation of School Performance Plans, 58.4% of all Rising Stars schools (SY 2017-2018) are utilizing effective strategies in each of the six standards in the Nevada Policy on Parental Involvement and Family Engagement. |
| Nevada Educator Performance Framework Professional Responsibilities’ Standard 4 score state average | Nevada Educator Performance Framework Professional Responsibilities’ Standard 4 score state average: 3.22 (SY 2016-2017) | Nevada Educator Performance Framework Professional Responsibilities’ Standard 4 score state average: - SY 17-18  3.38 - SY 18-19  3.55 - SY 19-20  3.73 - SY 20-21  3.91 | Nevada Educator Performance Framework Professional Responsibilities’ Standard 4 score state average: - SY 17-18  3.23 |
| Chronic absenteeism rate in Nevada | Chronic absenteeism rate in Nevada: 17.18% (SY 2016-2017) | 10% reduction in chronic absenteeism year over year: - SY 17-18  15.46% - SY 18-19  13.92% - SY 19-20  12.52% - SY 20-21  11.27% | Chronic absenteeism rate in Nevada: 19.49% (SY 2017-2018) |

## Objective 9 – Internal Systems & Effectiveness

Student achievement could not happen without strong internal systems which recognize an effective and efficient distribution of funds. These systems are continuously improved upon by using internal audit findings and defined roles and expectations for the guardians and recipients of awarded funds. To ensure an effective distribution of resources to our education programs, our internal systems have policies and procedures for awarding grants, work programs, contracts, and supporting internal stakeholders to meet expectations.

### Strategy 9.1: Modernize audit methodologies utilizing technology.

- Strategy 9.2: Build internal systems and effectiveness.

- Strategy 9.3: Fiscal stewardship responsive to internal audits.

| Metrics | Baseline Data (SY 2016-17) | Five-Year Goal (SY 2020-21) | ………..Annual Progress |
| --- | --- | --- | --- |
| - Percentage of audit work performed at pre-audit stage (including desk audit) | - 60% with a 2018-2019 goal of 75% |  100% of audit work performed at pre-audit stage (including desk audit) | - Gathered baseline data |
| - Decrease grants providing funding awards untimely within fiscal/grants control - Eliminate stale claims within NDE control - Decrease stale claims above $50k | FY18: 20% of grant awards provided by July 1 FY18: 75 stale claims totaling $18M | - Zero grants receiving funding awards late within fiscal/grants control - Zero stale claims within NDE control - Reduce stale claims above $50k by 75% | - Twice yearly grants meetings hosted by fiscal/grants - Gathered baseline data |
| - Percentage of grants providing balanced checkbook each month (including spending status) | 30% of grants providing balanced checkbook each month | - 98% of grants providing balanced checkbook each month | - Approaching 2018-2019 goal of 85% of balanced checkbooks through training - Checkbooks 2.0 being built |
| - Decrease number of repeat audit findings - Decrease number of unsuccessful BOE contract submissions - Decrease number of unsuccessful IFC work program submissions | - 9 audit findings - Rerelease of policies and procedures with supported training in 2018 | - 100% compliance with 0 repeat audit findings - 100% of contracts submitted timely & accurately - 100% work programs submitted timely & accurately | - Gathered baseline data and set a goal of 50% reduction in repeat audit findings for 2018-2019 - Collaboration with other offices for systems training (contract & work program) |

## Objective 10 – Funding & Reporting

Objective 10: Funding & Reporting

The Department’s goals for student achievement cannot be accomplished in isolation of outside stakeholders which begets the need for an externally-facing fiscal goal. Objective 10: Funding & Reporting utilizes feedback from audit findings and grant awards to increase compliance by reducing errors and increasing equity by awarding monies competitively.

- Strategy 10.1: External Reporting

- Strategy 10.2: Funding Methodologies

| ………Metrics | Baseline Data (SY 2016-17) | Five-Year Goal (SY 2020-21) | Annual Progress |
| --- | --- | --- | --- |
| - Number of substantive school funding errors in final funding or published information/calculations | - 6 school funding errors, with the 2018-2019 goal of 3 errors | - 0% errors | - Gathered baseline data for 2016-2017 |
| - All charter schools appropriately recognized within funding model | - Charter schools inappropriately accounted for within model | - Support definition and implementation of new public school funding model | - 6 DSA equity allocation meetings hosted in preparation for 2019 legislative session |

## Objective 11 – Students and Adults Develop Social and Emotional Competencies

Studies have shown that social and emotional learning (SEL) is essential for student success in schools and after graduation. Industry considered “risky behaviors” such as drug use, bullying, and absenteeism are often linked to poor social and emotional skills. SEL has been linked to improved performance within the classroom and on academic assessments.

- Strategy 11.1: Office for a Safe and Respectful Learning Environment is responsive and proactive to the needs and goals of NRS 388.

  - Strategy 11.2: Systems promote and nourish safe school environments for all.

  - Strategy 11.3: Systems actively promote for staff and students equitable social, emotional, and academic development (free from racial, economic, religious, gender, or ability biases).

  - Strategy 11.4: Systems support and promote district and school implementation of equitable multi-tiered system of supports.

  - Strategy 11.5: Systems promote healthy staff and students.

| Metrics | Baseline Data (SY 2015-16) | Five-Year Goal (SY 2020-21) | Annual Progress |
| --- | --- | --- | --- |
| - Increase in Social Emotional indicators on Climate Survey | National Benchmarks Set 1) Cultural and Linguistic Competency 2) Relationships 3)Physical Safety 4) Emotional Safety 100 - 299 - Least favorable conditions 300 - 400 - Favorable conditions 401 - 500 - Most favorable conditions | - All school districts have adopted SEL Standards - Increase indicators by 10% | - Nevada students have been reporting increasingly positive perceptions of their school climate across all domains measured (Cultural and Linguistic Competence, Relationships, Emotional Safety, and Physical Safety). - On average across the state, students feel that their school’s climate is favorable (scores between 300 and 400 indicate a favorable environment). - Students feel more positive about the physical safety of their school environment (378) compared to the emotional safety (338). |
| - Increase safety within schools by adding social workers, MTSS, and SEAD | - Currently incorporated in several schools | - All school districts adopted SEL Standards - Increase social workers, MTSS, and SEL adoption in schools by 5% year over year | - Increase in social workers by 300% for 2017-2018 - Increase in license clinical social workers intern by 100% in 2018-2019 - Doubled the number of schools trained from year 1 to year 2 of implementation. |
| - Reduction reported behavioral violence toward staff and students - Decrease in expulsions and suspensions | Base line 2015-16 Violence to students: 8415 Violence to Staff: 855 Weapons: 953 Controlled Substance: 154 Use of Alcohol: 427 | Slow and reduce upward trend | 2016-17 Violence to students: 869 Violence to Staff: 876 Weapons: 990 Controlled Substance: 192 Use of Alcohol: 405 2017-18 Violence to students: 11,187 Violence to Staff: 876 Weapons: 1040 Controlled Substance: 187 Use of Alcohol: 470 |
| - Decrease in bullying trend data - Decrease of chronic absenteeism | Base line 2015-16 Bullying: 8203 Cyberbullying: 511 | Decrease trend | 2016-17 Bullying: 3497 Cyberbullying: 430 2017-18 Bullying: 5459 Cyberbullying: 524 |

## Objective 12 – Multi-Tiered System of Support & Department Climate Goal

The Department has both external Fastest Improving and internal State Board goals that reflect an urgency to support students and school leaders in achievement. Such a significant change in our LEAs could not be coupled without an inward goal that asks the Department to grow with those they support. Selecting a climate goal improves our internal procedures as the Department takes on the ambitious work of becoming the Fastest Improving State in the Nation. Notably, it also addresses equity and acting upon stakeholder feedback which is thematic throughout the Common Problems and Objectives sections of the STIP.

- Strategy 12.1: Employ MTSS framework to increase Department collaboration to impact student achievement for all.

  - Strategy 12.2: Demonstrate equity across all Department members to strengthen programs from increased engagement and a reflection of equity for all students.

  - Strategy 12.3: Elevate Department climate based on staff feedback.

| Metrics MetricM…………Metrics | Baseline Data (2018) | Five-Year Goal (SY 2020-21) | Annual Progress |
| --- | --- | --- | --- |
| MTSS used across offices to for successful deployment of Department programs | Zero offices using MTSS framework to collaborate and deploy programs | All Department offices using MTSS to collaborate and deploy programs | 1 team using MTSS Created MTSS Leadership Team produced district document |
| Increase clear communication across Department Increase clarity around work roles | MTSS committee determined clear communication and clear work roles as a priority for 2018 | MTSS committee selects 2 indicators annually to improve year over year | Hosted feedback huddles, Coffee with the Chief, and Icebreaker Lunches to create more equitable dialogue Created SmartSheet and trained all AA’s for District Communication tool and newsletter for district for one stop shop for Department information |
| Department survey and huddle data to reflect improved climate year over year (an improvement in the previous year’s focus areas) | - Baseline data gathered from feedback huddles and surveys to identify areas for climate improvement in 2018-2019 | - Department survey and huddle data to reflect improved climate year over year (an improvement in the previous year’s focus areas) | Created Climate team to host feedback huddles to determine how to elevate department climate Department values created Created a response to “consistent onboarding” being an issue for staff as reported by survey results |

# SECTION 4: INFORMATION CONCERNING SUCCESS AFTER GRADUATION

State law requires this plan to include strategies (see “Strategies for Improvement,” below) to provide information in the areas of admission requirements for institutions of higher education, opportunities for financial aid, the Governor Guinn Millennium Scholarship, and preparation for success after graduation. These strategies are integrally aligned with the Governor’s vision of “all students, regardless of zip code, have access to a high-quality education,” and “all educators supported and respected for their profession.”

Additionally, the state of Nevada offers a number of programs that help prepare students for post-secondary success:

- Nevada College Savings Plans Program

- Nevada Prepaid Tuition Program

- Governor Guinn Millennium Scholarship Program

- Nevada College Kick Start Savings Program

- Nevada GEAR UP program

- Articulated college credit programs

- GoToCollegeNevada.org campaign

# SECTION 5: ALLOCATION OF RESOURCES/BUDGET

State law requires this plan to include an analysis of and strategies to improve the allocation of financial resources dedicated to P-12 public education. However, much of the data required is not currently available to the Department because certain requirements of NRS 386.650 concerning the automated system of accountability information have never been met; specifically, the automated system does not have the capacity to fully access financial accountability information for each public school, for each school district, and for this state as a whole. The Department, therefore, proposes the following baseline strategies and the continuation of exploratory work begun in 2014 to begin the work of better analyzing how the allocation of State resources actually improves the academic achievement of pupils.

## Strategies for Improvement

| STRATEGY | STAFF LEAD | TIMELINE |
| --- | --- | --- |
| Implement the Governor’s vision that every student, regardless of zip code, will have access to a high-quality education. | Superintendent Ebert and Deputy Superintendent Moore | 2019-2021 Biennium |
| Implement the Governor’s vision to give educators the respect and resources they deserve. | Superintendent Ebert and Deputy Superintendent Dietrich | 2019-2021 Biennium |
| Breakdown silos within and between Department offices. | Deputy Superintendents Moore, Dietrich, and Fiscal and Thirsty for Change Staff Cabinet | 2019-2021 Biennium |
| Convene with job-alike stakeholders across the state and provide meaningful development aligned to the Department’s STIP. | Deputy Superintendents Moore, Dietrich, and Fiscal | 2019-2021 Biennium |
| Implement Budget Account 2698 for School Safety Task Force to the Governor and Task Forces’ recommendations. | Director McGill and Office of Safe and Respectful Learning Environments | 2019-2021 Biennium |
| Improve State and Federal spend-down rates in Districts by 20% year over year. | Superintendent Ebert and Deputy Superintendents Moore, Dietrich, and Fiscal | 2019-2021 Biennium |

## Budget Impact of This Plan

The provisions of this plan are within the Governor’s Recommended Budget for the 2020-2021 biennium for the Department of Education.